## Read me
AlcorOne — office fit-out BOQ template and specification pack
Free to use, copy, and take to any contractor. Using it puts you under no obligation to AlcorOne, and no part of it needs us.
What is in here
BOQ format (blank) — the eleven-column format with office lines pre-listed under the four heads of a fit-out — builder's work, MEP, HVAC, furniture — plus the boundary lines that decide what the number covers.
Worked sample — a 4,000 sq ft carpet-area floor planned for about 50 seats, filled to the level of detail that counts as specified. An illustrative floor, not a client's project.
Specification reference — fifteen elements: what each line must name, the vague wording to refuse, and the failure that vagueness causes.
Office fit-out checklist — questions to settle before signing, at test fit, on site and at handover. Printable.
Measurement basis
Office fit-outs are compared per sq ft of carpet area. State that basis at the top, and state which of the four heads — builder's work, MEP, HVAC, furniture — the number covers: a rate that excludes HVAC and furniture is not a lower price, it is a smaller scope. Partitions are measured per sq ft of face with the height stated, or per running foot with the height stated. A per-seat figure is not a rate; it falls out of the per-sq-ft number and the seating density.
Why the rate column is empty
On purpose. This sheet is for putting two or three contractors' numbers side by side against one fixed specification, and pre-filled rates would anchor that comparison. Cost bands, with their basis and their date attached, are published on the site instead.
Read next
Office fit-out cost per sq ft of carpet area, by grade, with its basis and date: https://www.alcorone.com/services/office-fitout-cost/
What a turnkey commercial fit-out covers, and what usually sits outside it: https://www.alcorone.com/services/turnkey-commercial-fitout/
How long an office fit-out takes, and what makes it late: https://www.alcorone.com/services/office-fitout-timeline/
The whole-home BOQ pack (blank format, 3BHK sample, carpenter checklist): https://www.alcorone.com/boq-template/
A note on contact
A download is not an enquiry, and we do not treat it as one. Nobody will call you for taking this file.
AlcorOne Solutions LLP · alcorone.com

## BOQ format (blank)
Blank format with the usual lines pre-listed. Give this to each contractor and ask them to quote on it — a quotation that arrives in your format is comparable; one that arrives in theirs is not. Shaded cells are theirs to fill. Add or delete lines; keep the columns.
S.No | Area / room | Item description | Unit | Qty | Core material and grade | Edge banding | Hardware — brand and series | Finish — brand and code | Rate (₹) | Amount (₹) | Remarks / exclusions
1 | Builder's work | Partitions — gypsum or block, height stated | sq.ft
2 | Builder's work | Glazed partitions and cabin fronts | sq.ft
3 | Builder's work | Doors with hardware | Nos
4 | Builder's work | Ceilings — grid and gypsum, by zone | sq.ft
5 | Builder's work | Flooring — by zone | sq.ft
6 | Builder's work | Painting and wall finishes | sq.ft
7 | Builder's work | Joinery — reception, storage, pantry counter | Nos
8 | MEP | Electrical distribution from landlord tap-off | Lot
9 | MEP | Raw power and UPS power points | Nos
10 | MEP | Lighting and controls | Nos
11 | MEP | Fire detection and suppression modifications | Lot
12 | MEP | Data and voice cabling — nodes | Nos
13 | HVAC | System, ducting, grilles, controls and commissioning | Lot
14 | Furniture | Workstations | Nos
15 | Furniture | Chairs, meeting tables, soft seating, storage | Nos
16 | Boundary | Access control, CCTV, AV, IT active — named or excluded | Lot
17 | Site | Preliminaries — protection, barricading, debris, working hours | Lot
18 | Handover | Snag closure, as-builts, test reports, warranties | Lot
Subtotal
GST @ 18%
Total
Measurement basis used in this document: ______________________ (state it once, use it on every line)
Quotation valid until: ____________ Completion period from start: ______ weeks
Excluded from this document entirely: ____________________________________________

## Sample — 4,000 sq ft floor
A 4,000 sq ft carpet-area floor planned for about 50 seats, with three cabins, two meeting rooms and a pantry, handed over as a bare shell with the landlord's power tap-off — an illustrative floor, not a client's project. Specifications are filled in hard because they are the part you lock. Rates are deliberately blank: the published office band carries its basis and date.
S.No | Area / room | Item description | Unit | Qty | Core material and grade | Edge banding | Hardware — brand and series | Finish — brand and code | Rate (₹) | Amount (₹) | Remarks / exclusions
1 | Builder's work | Partitions — gypsum on metal studs, cabins and meeting rooms | sq.ft | 1,100 | Board brand and thickness, stud gauge and spacing named; acoustic infill named for meeting rooms | — | — | Paint system named |  |  | Height stated: to the slab for meeting rooms, so sound cannot pass over the top.
2 | Builder's work | Glazed cabin and meeting-room fronts | sq.ft | 420 | Toughened glass: thickness, single or double glazed, frame system named | — | Door patch fittings and closer: brand and model named | Manifestation film named
3 | Builder's work | Doors with hardware | Nos | 7 | Door core and frame named | — | Hinges, lock, handle and closer: brand and model named | Finish named |  |  | Fire-rated doors named separately if the building requires them.
4 | Builder's work | Ceilings — mineral fibre grid in open office, gypsum in cabins and corridor | sq.ft | 3,600 | Grid and tile brand, tile size and acoustic rating named; gypsum to IS 2095 (Part 1) on GI framing | — | — | — |  |  | Tiles removable over services; access panels in gypsum zones.
5 | Builder's work | Flooring — carpet tile in open office, vinyl in pantry | sq.ft | 3,800 | Product, brand, thickness and wear rating named per zone; underlay named | — | — | Colour codes named |  |  | Floor levelling of the shell stated as included or excluded.
6 | Builder's work | Painting and wall finishes | sq.ft |  | Putty, primer and finish coats stated | — | — | Brand and shade named |  |  | Feature walls on their own line.
7 | Builder's work | Joinery — reception counter, storage, pantry counter | Nos | 4 | Board grade per item: BWP to IS 710 in the pantry, BWR to IS 303 elsewhere | 2mm PVC exposed | Hinges and channels: brand and series named | Laminate or veneer named |  |  | Pantry appliances excluded — power and plumbing to them included.
8 | MEP | Electrical distribution from the landlord's tap-off | Lot | 1 | DB and breakers: make and rating named; FR-LSH wire brand named; containment named | — | — | — |  |  | Starts at the tap-off — anything upstream is landlord scope.
9 | MEP | Raw power and UPS power points | Nos |  | Points per workstation stated; raw and UPS circuits kept separate | — | Socket brand and series named | — |  |  | UPS unit itself named, or excluded.
10 | MEP | Lighting and controls | Nos |  | Fittings: brand, model, wattage and colour temperature named; controls named | — | — | — |  |  | Lux level the layout is designed to, stated.
11 | MEP | Fire detection and suppression modifications | Lot | 1 | Detectors and sprinkler heads relocated or added, to the building's system | — | — | — |  |  | Building's fire consultant and their approval named as a dependency.
12 | MEP | Data and voice cabling | Nos | 60 | Cable category, brand and containment named; nodes counted and labelled | — | — | — |  |  | Switches, access points and servers excluded — tenant's IT.
13 | HVAC | Air conditioning within the demise | Lot | 1 | System type and capacity named; ducting, grilles, thermostats; commissioning and balancing report | — | — | — |  |  | If the building supplies chilled water or an AHU, the boundary point is named.
14 | Furniture | Workstations — linear, with screens and storage | Nos | 46 | System and brand named; desktop size and board grade named | — | Cable management named | Finish named |  |  | Power and data at each desk on the MEP lines.
15 | Furniture | Chairs, meeting tables, soft seating, storage | Nos |  | Model and supplier named for each item | — | — | — |  |  | Listed item by item, not as a furniture allowance.
16 | Boundary | Access control, CCTV, AV | Lot |  | Named with make and scope, or written as excluded | — | — | — |  |  | Requirements vary widely between tenants — never assumed inside the rate.
17 | Site | Preliminaries | Lot | 1 | Floor and lift protection, barricading, debris removal, permitted working hours | — | — | — |  |  | After-hours working, if the building requires it, priced here.
18 | Handover | Handover documents | Lot | 1 | Closed snag list, as-built drawings, electrical layout, test reports, warranties with models named | — | — | — |  |  | Agreed at contract stage, not assembled on the day.
Subtotal
GST @ 18%
Total
Measurement basis used in this document: ______________________ (state it once, use it on every line)
Quotation valid until: ____________ Completion period from start: ______ weeks
Excluded from this document entirely: ____________________________________________

## Specification reference
What each line must name. The third column is the wording to refuse.
Element | What the line must name | The vague version | Why it matters
Measurement basis | Carpet area in sq ft for the overall rate; partitions by face area or rft with the height stated | Basis unstated, or a per-seat figure | A per-seat number moves with density without the rate changing, so it cannot compare quotes.
Scope heads | Which of builder's work, MEP, HVAC and furniture the number covers, line by line | "Turnkey" | A rate that excludes HVAC and furniture is not a lower price; it is a smaller scope.
Shell condition and landlord boundary | The shell condition at handover, and where landlord scope ends for power, HVAC and fire | "Ready shell" | A bare shell and a warm shell are different projects at the same stated rate.
Partitions | Board and stud specification, acoustic infill, and height — to ceiling or to slab | "Gypsum partition" | A partition that stops at the false ceiling lets meeting-room sound pass over the top.
Glazing and doors | Glass thickness and type, single or double glazed, frame system, door hardware by model | "Glass partition" | Glass type and glazing decide both safety and acoustic privacy.
Ceilings | Grid and tile brand, size and acoustic rating; gypsum zones and access panels | "Grid ceiling" | Tile rating sets the noise level of an open floor; services above need access.
Flooring | Product, brand, thickness and wear rating per zone; levelling and underlay | "Carpet tile" | Wear rating decides whether walkways show tracks within a year.
Electrical distribution | Starting point at the landlord's tap-off; DB and breaker make and rating; wire grade | "Electrical work" | Anything upstream of the tap-off is landlord scope; unstated, it becomes a dispute.
Raw and UPS power | Points per workstation, raw and UPS circuits separated, UPS unit named or excluded | "Power points" | Mixed circuits put desk equipment on the same supply as pantry appliances.
Lighting | Fittings by brand and model, colour temperature, controls, design lux level | "LED lighting" | Catalogue panels and specified fittings sit grades apart in cost and in result.
Fire detection and suppression | What is relocated or added, to whose system, and the building consultant's approval | "Fire as per norms" | Modifying the base system pulls the building's consultant onto the critical path.
Data and voice | Cable category and brand, node count, containment; active equipment excluded by name | "Networking" | Cabling is fit-out scope; switches and access points are not — say so.
HVAC | System type and capacity, ducting and terminals, commissioning and balancing report, boundary with building plant | "AC as required" | HVAC is a large sum sitting on the landlord boundary; name which side each part is on.
Furniture | Workstation system and size, chair and table models, listed item by item | "Furniture allowance" | An allowance is a number with no specification behind it.
Approvals and GST | Who submits, who pays fees and deposits, what happens if approval is late; subtotal, GST, total | Not mentioned | An approval delay with no agreed consequence becomes a dispute rather than a variation.

## Checklist
Office fit-out checklist — questions for your contractor
Print this. Ask them on site, in this order, and write the answers on the sheet. An answer you cannot write down is not an answer.
Before signing
☐ | Have you read the building's fit-out guide and our lease obligations?
☐ | What shell condition is the landlord handing over, and where does their scope end?
☐ | Which of builder's work, MEP, HVAC and furniture is in your number, line by line?
☐ | Who submits the fit-out drawings for approval, who pays the fees and deposit, and what happens to price and programme if approval is late?
☐ | Is the occupancy date fixed? If so, what does that do to the programme and the rate?
At test fit and design
☐ | How many seats does the layout give, and at what sq ft per seat?
☐ | Do meeting-room partitions go to the slab?
☐ | How many power and data points per desk, and are raw and UPS circuits separate?
☐ | Which long-lead items — glazing, HVAC, furniture — need ordering first?
On site
☐ | What working hours does the building permit, and is after-hours work priced?
☐ | Has the building's fire consultant been engaged, and when do they need to sign off?
☐ | Are selection changes after start priced as variations before they are done?
At handover
☐ | Is the snag list written and closed, with a date on anything open?
☐ | Do we have as-built drawings and the final electrical layout?
☐ | Are the HVAC commissioning report and electrical test results handed over?
☐ | Are warranties handed over with the models actually fitted named?
Money
☐ | What triggers each payment — a stage we can inspect?
☐ | How is a variation priced, and do we see the price before the work is done?
☐ | Is GST included in the figure you just said?